## 12-Month Project Gantt Chart
גאנט תכנון לפרויקט - מערכת למציאת Fake News באמצעות AI
| Q1 | [14 empty] | Q2 | [14 empty] | Q3 | [12 empty] | Q4
| JANUARY |  |  |  |  | FEBRUARY |  |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  |  | MAY |  |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER
| 6 | 13 | 20 | 27 |  | 3 | 10 | 17 | 24 |  | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 |  | 4 | 11 | 18 | 25 |  | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26
PROJECT WEEK | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
פרק 1
דוח אפיון
פרק 2
סביבת עבודה ובניית השלד
פרק 3
אלגוריתמיקה סדרת אימון
פרק 4
סדרת מבחן וסביבת WEB
פרק 5
ניתוח משתמש
פרק 6
המשך פיתוח סביבת WEB ויצור production
פרק 7
תוסף Chrome
פרק 8
בדיקות סופיות
פרק 9
ספר פרויקט
פרק 10
סיום
PROJECT END
תקופת מבחנים - סמסטר א'
תקופת מבחנים - סמסטר ב'

## BLANK - 12-Month Project Gantt
12-MONTH PROJECT GANTT CHART TEMPLATE
Enter the date of the first Monday of each month ----> | Q1 | [14 empty] | Q2 | [14 empty] | Q3 | [12 empty] | Q4
| JANUARY |  |  |  |  | FEBRUARY |  |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  |  | MAY |  |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  |  | DECEMBER
| 6 | 13 | 20 | 27 |  | 3 | 10 | 17 | 24 |  | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 |  | 4 | 11 | 18 | 25 |  | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28
PROJECT WEEK | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
PHASE ONE
Project Conception and Initiation
PHASE TWO
Project Definition and Planning
PHASE THREE
Project Launch of Execution
PHASE FOUR
Project Performance and Control
PHASE FIVE
Project Close
PROJECT END
Project Charter
Plan Review
Initiation
Scope and Goal Setting
Budget
Work Bkdwn Structure
Gantt
Chart
Communication Plan
Risk Management
Forecasts
Quality
KPIs
Status and Tracking
Objective Execution
Quality Deliverables
Effort and Cost Tracking
Performance
Postmortem
Project Punchlist
Report
TODAY

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.